## Project Calender
PROJECT CALENDAR/GANTT CHART
ACTIVITY | START DATE | DURATION (IN DAYS) | END DATE | PREDECESSORS
1.1 Project team | 2024-09-01 | 3 | 2024-09-04 | NULL
1.2 Assign Roles and Responsibilities | 2024-09-04 | 4 | 2024-09-08 | 1.1
1.3 Form project plan | 2024-09-09 | 7 | 2024-09-16 | 1.2
1.4 Define project scope, objectives and success criteria | 2024-09-17 | 14 | 2024-10-01 | 1.3
1.5 Liaise with university administration | 2024-10-02 | 14 | 2024-10-16 | 1.4
2.1 Secure Venue | 2024-10-17 | 14 | 2024-10-31 | 1.5
2.2 Design Seating Layout | 2024-11-01 | 3 | 2024-11-04 | 2.1
2.3 Stage setup & podium | 2025-05-17 | 7 | 2025-05-24 | 2.1
2.4 Sound & Lighting | 2025-05-21 | 3 | 2025-05-24 | 2.2/2.3
2.5 Signage & Directional Boards | 2025-05-19 | 5 | 2025-05-24 | 2.1
2.6 Co-ordinate with on-site security | 2025-05-22 | 1 | 2025-05-23 | 1.5
3.1 Design invitation cards & digital invitations | 2024-11-24 | 11 | 2024-12-05 | 2.1
3.2 Develop guest list | 2024-12-06 | 7 | 2024-12-13 | 3.1/5.2
3.3 Print & distribute invitations | 2024-12-14 | 14 | 2024-12-28 | 3.3
3.4 Co-ordinate with alumni for special guests | 2024-12-29 | 2 | 2024-12-31 | 1.5
4.1 Vendor selection | 2025-01-01 | 14 | 2025-01-15 | 3.3
4.2 Finalise menu | 2025-01-16 | 3 | 2025-01-19 | 4.1
5.1 Open graduation registration portal | 2025-01-20 | 30 | 2025-02-19 | 3.3
5.2 Verify graduate details | 2025-02-20 | 14 | 2025-03-06 | 5.1
5.3 Name cards & certificates | 2025-03-07 | 14 | 2025-03-21 | 5.2
5.4 Seating arrangements | 2025-03-22 | 2 | 2025-03-24 | 5.2
5.5 Distribute graduation attire | 2025-05-21 | 3 | 2025-05-24 | 5.3
5.6 Ceremonial Procedures | 2025-05-22 | 2 | 2025-05-24 | 5.5
6.1 Co-ordinate with university media teams | 2025-03-23 | 14 | 2025-04-06 | 1.5
6.2 Photographers & Videographers | 2025-04-07 | 7 | 2025-04-14 | 6.1
6.3 Live Stream Equipment | 2025-04-15 | 7 | 2025-04-22 | 6.2
6.4 Test sound systems | 2025-05-20 | 4 | 2025-05-24 | 6.3
7.1 Implement contingency plans | 2025-05-10 | 14 | 2025-05-24 | 1.4
8.1 Post Evaluation | 2025-05-26 | 3 | 2025-05-29 | 7.1
8.2 Archive Documentation & Reports | 2025-05-30 | 7 | 2025-06-06 | 8.1
Formulas:
END DATE = ([START DATE]+[DURATION (IN DAYS)])
START DATE = ([END DATE, row above])

## Priority Levels
TASK ID | TASK | DURATION(DAYS) | ES | EF | LS | LF | SLACK | PREDECESSORS | PRIORITY LEVEL | FAST-TRACKING NOTES
1.1 | Form Project Team | 3 | 1 | 3 | 1 | 3 | 0 | NULL | High
1.2 | Assign Roles & Responsibilities | 4 | 4 | 8 | 4 | 8 | 0 | 1.1 | High
1.3 | Form Project Plan | 7 | 9 | 16 | 9 | 16 | 0 | 1.2 | High
1.4 | Define project scope, objectives & success criteria | 14 | 17 | 31 | 17 | 31 | 0 | 1.3 | High
1.5 | Liaise with university administration | 14 | 32 | 46 | 32 | 46 | 0 | 1.4 | High
2.1 | Secure venue | 14 | 47 | 61 | 47 | 61 | 0 | 1.5 | High
2.2 | Design seating layout | 3 | 61 | 64 | 61 | 64 | 0 | 2.1 | Medium
2.3 | Stage setup and podium | 7 | 64 | 71 | 64 | 71 | 0 | 2.1 | Medium
2.4 | Sound & Lighting | 3 | 71 | 74 | 71 | 74 | 0 | 2.2/2.3 | Low | Can overlap with 2.3
2.5 | Signage & Directional Boards | 5 | 74 | 79 | 74 | 79 | 0 | 2.1 | Low
2.6 | Co-ordinate with on-site security | 1 | 79 | 80 | 79 | 80 | 0 | 1.5 | Medium
3.1 | Design invitation cards & digital invitations | 11 | 81 | 92 | 81 | 92 | 0 | 2.1 | High
3.2 | Develop guest list | 7 | 82 | 89 | 82 | 89 | 0 | 3.1/5.2 | High
3.3 | Print & distribute invitations | 14 | 89 | 103 | 89 | 103 | 0 | 3.3 | High
3.4 | Co-ordinate with alumni for special guests | 2 | 103 | 105 | 103 | 105 | 0 | 1.5 | High
4.1 | Vendor selection | 14 | 105 | 119 | 105 | 119 | 0 | 3.3 | Medium
4.2 | Finalise menu | 3 | 119 | 122 | 119 | 122 | 0 | 4.1 | High
5.1 | Open graduation registration portal | 30 | 123 | 153 | 123 | 153 | 0 | 3.3 | High | This could overlap with 1.5 saving at least 7 days
5.2 | Verify graduate details | 14 | 154 | 168 | 154 | 168 | 0 | 5.1 | High
5.3 | Name cards & certificates | 14 | 169 | 183 | 169 | 183 | 0 | 5.2 | High | This could overlap with 5.2 saving at least 5 days
5.4 | Seating arrangements | 2 | 184 | 186 | 184 | 186 | 0 | 5.2 | Medium
5.5 | Distribute graduation attire | 3 | 186 | 189 | 186 | 189 | 0 | 5.3 | Medium
5.6 | Ceremonial Procedures | 2 | 190 | 192 | 190 | 192 | 0 | 5.5 | Medium
6.1 | Co-ordinate with university media teams | 14 | 192 | 206 | 192 | 206 | 0 | 1.5 | High | Could be done in around 10 days
6.2 | Photographers & Videographers | 7 | 207 | 221 | 207 | 221 | 0 | 6.1 | High
6.3 | Live Stream Equipment | 7 | 222 | 229 | 222 | 229 | 0 | 6.2 | High
6.4 | Test sound systems | 4 | 230 | 234 | 230 | 234 | 0 | 6.3 | High | This could overlap with 6.3 saving about 2 days
7.1 | Implement contingency plans | 14 | 235 | 249 | 235 | 249 | 0 | 1.4 | Medium
8.1 | Post Evaluation | 3 | 250 | 253 | 252 | 255 | 3 | 7.1 | High
8.2 | Archive Documentation & Reports | 7 | 254 | 261 | 255 | 262 | 1 | 8.1 | High

## Resource Sheet
RESOURCE | DETAILS | COST
Project Staff | Salaries | 50000
Project Plan | Software, Tools | 1000
Venue | Décor of entire venue, seats | 100000
Signage and Boards | The directional signs and boards, etc | 1000
On-site personel | Staff who will be at the venue, overseeing everything | 25000
Sound & Lighting | Equipment and Technicians | 3000
Invitation Cards | Software, Tools, Postage | 3000
Vendor | Food, Drinks, Treats | 45000
Graduation Attire | Material and Tailor | 7000
Photographers & Videographers, Livestreaming | Services | 4000
Contingency Fund | Backup services | 20000
Certificates and Name Cards | Printing | 2500
University Staff/Volunteers | Salaries | 2500
TOTAL COST |  | 264000

## Milestones
MILESTONE | TARGET DATE | DESCRIPTION
Project Team created and Roles are assigned | 2024-09-08 | This is where the project team was organised. Each member got a role and task that they had to complete for the event.
Project Plan was created | 2024-09-16 | All things regarding the project was put into place.
Project Scope was implemented | 2024-10-01 | The project scope was implemented and this was the official starting point of the project
Venue was secured | 2024-10-31 | The venue was booked for the graduation day
Invitation cards were created | 2024-12-05 | Invitations were finally designed and in preparation to get sent out
Invitation cards were sent out | 2024-12-28 | Invitations were sent out making all esteemed guests aware of the event.
Vendors and menu were finalised | 2025-01-19 | All food, refreshments, treats are taken care of with notes of dietry concerns and allergens
Graduation registration portal was opened | 2025-02-19 | This allowed guests to confirm their attendence
Name cards & graduation cards were developed | 2025-03-21 | Certificates and namecards of graduates were created, ready for the big day
Media was organised | 2025-04-22 | Photographers, videographers, sound, lighting and broadcasters were ready
Event took place | 2025-05-25 | Event sucessfully took place
Post Evaluation | 2025-05-29 | A wrap up meeting concluding all things graduation were concluded.